## Sheet 1
PRIMARY DC | GSO (Greensboro, NC – Primary On-Premises Data Center) P Series Frames (Power 9/10 – AIX-based): E950-01-9040-MR9 (Power 9), S924-01-9009-42G (Power 9) – no explicit decom in plan, but linked apps mapped iSeries Partitions: Majority– several in decom plan. App Mapping (with Decom Details):
| Application Category | Frames/Partitions | Frame Serial Number and Type | Environment | Decom Status | Remarks
| SAP (Core ERP) | RLIP1EUD, RLIP1EUB, RLIP1ETP, RLIP1EUA, RLID2SAP, RLID1SAP, RLIS1SAP, RLIQ2ED1, RLIG2EUT | N/A (I Series) | Prod/Dev/QA/Test | Plan to Decomm in 12 to 18 Months (some DEV) | DEV servers like RLID2SAP targeted; Prod (RLIP1EUD) not in plan – critical, retain/migrate
| PKMS (Warehouse Management) | SYSG, SYSGTEST, RLSYS01, RLIP1PKG, RLID1PKG, RLIQ1PKG, RLIT4GEN, DBMSYS01, DBMP1PKG | N/A (I Series) | Prod/Test/Dev/QA | Plan to Decomm in 12 to 18 Months (DEV/QA) | DEV like RLID1PKG planned; Prod (SYSG) not – logistics critical, Modernize first
| EDI (Electronic Data Interchange) | RLID1EDI, RLIP1EDI | N/A (I Series) | Dev/Prod | Plan to Decomm in 12 to 18 Months (DEV) | RLID1EDI DEV targeted; Prod retain
| GFE (Global Front End) | RLID1GFE, RLIQ1GFE, RLIP1GFE | N/A (I Series) | Dev/QA/Prod | Plan to Decomm in 12 to 18 Months (DEV/QA) | RLID1GFE DEV planned; Prod retain
| Aldon (Change Management) | RLIP1ARC, RLIP1ESM | N/A (I Series) | Prod | Not in plan | Prod – retain or Modernize
| IP / General Infra | GSOTEST2, RLID1IPX, RLIQ1IPX, SYSBLON, SYSB | N/A (I Series) | Test/Dev/QA/Prod | Plan to Decomm in 12 to 18 Months (some DEV) | DEV like RLID1IPX targeted
| Infra / Testing | RLIP2LPH, RLIS2ADM, RLIP1GSO, GSOTEST | N/A (I Series) | Prod/Test | Plan to Decomm in 12 to 18 Months (Test) | RLIS2ADM Test planned
| Enterprise Planning | RLAD1JEP, RLAD2JEP | N/A (P Series) | DEV | Plan to Decomm in 12 to 18 Months | DEV – low risk decom
| Microstrategy & Crystal Reports | RLAD1GBI | N/A (P Series) | DEV | Plan to Decomm in 12 to 18 Months | DEV – reporting legacy
| Reconnect | RLAD1GCM | N/A (P Series) | DEV | Plan to Decomm in 12 to 18 Months | DEV – integration legacy
| JDA Allocation | RLAD1DBH | N/A (P Series) | DEV | Plan to Decomm in 12 to 18 Months | DEV – allocation legacy
| PLM (Product Lifecycle Management) | RLAD1PLM | N/A (P Series) | DEV | Plan to Decomm in 12 to 18 Months | DEV – lifecycle legacy
| Informatica Metadata EDM/ETL | RLAD1EDM | N/A (P Series) | DEV | Plan to Decomm in 12 to 18 Months | DEV – ETL legacy
| MQ Messaging | RLAD1MQS, RLAD2MQS | N/A (P Series) | DEV | Plan to Decomm in 12 to 18 Months | DEV – messaging legacy
| Logility | RLAD1LGY | N/A (P Series) | DEV | Plan to Decomm in 12 to 18 Months | DEV – supply chain legacy
| UNIX Testing | RLAD1ADM, RLAD2ADM, RLAD4ADM | N/A (P Series) | DEV | Plan to Decomm in 12 to 18 Months | DEV – testing legacy
| Virtualization (iSeries-VIOS) | RLAGGVS1, RLAGGVS2 | ELLE-9105-42A-78A7361 (I Series) | Running | Not in plan | Running – retain for virtualization
DR SITE | DR-Denver (Disaster Recovery Site – On-Premises Secondary) P Series Frames (Power 8 – AIX-based): 8286-42A-SN217473V (P Series) – not in plan iSeries Partitions: Backup/HA pairs App Mapping (with Decom Details):
| Application Category | Frames/Partitions | Frame Serial Number and Type | Environment | Decom Status | Remarks
| SAP (Core ERP) | RLIH1EUD, RLIH1EUB, RLIH1ETP, RLIH1EUA, RLIH1BUA | N/A (I Series) | HA/Backup | Not in plan (Prod HA) | Prod DR – critical, retain
| PKMS (Warehouse Management) | BUSYS01, HASYS01, BUP1PKG, HAP1PKG, HASYSG, BUSYSG | N/A (I Series) | HA/Backup | Not in plan (Prod HA) | Prod DR – retain
| EDI | BUP1EDI, HAP1EDI | N/A (I Series) | HA/Backup | Not in plan | Prod DR – retain
| GFE | RLIH1GFE | N/A (I Series) | HA/Backup | Not in plan | Prod DR – retain
| Aldon | BUP1ESM, HAP1ESM, BUP1ARC, HAP1ARC | N/A (I Series) | HA/Backup | Not in plan | Prod DR – retain
| IP / General Infra | BUSYSB, HASYSB, BUBLON, HABLON | N/A (I Series) | HA/Backup | Not in plan | Prod DR – retain
| Infra / Testing | RLIH1GSO | N/A (I Series) | HA/Backup | Not in plan | Prod DR – retain
| Enterprise Planning | RLAD1JEP, RLAD2JEP (linked DR) | N/A (P Series) | DEV | Plan to Decomm in 12 to 18 Months | DEV – low risk, but check DR dependencies
| (Other AIX apps) | Similar to GSO (e.g., RLAD1GBI DR mirrors) | N/A (P Series) | DEV | Plan to Decomm in 12 to 18 Months | DEV – align with GSO decom
NOTES | Key Insights from Remapping Decom Focus: Primarily DEV/QA AIX in GSO (12–18 months) – low risk, but check Prod dependencies. Prod/HA/Backup (e.g., SAP/PKMS in DR-Denver) not targeted – critical, retain/Modernize. Serial Coverage: Limited – only ~10–15 have explicit serials (e.g., ELLE-9105-42A-78A7361 for RLAGGVS1); N/A for most partitions (data gaps). Alignment to KCMI: Reinforces "Modernize" for SAP/PKMS (migrate iSeries to Azure); "Kill" for DEV AIX legacy. Insights: GSO dominates (high concentration risk); DR-Denver is pure resilience (no new builds). Recommend validating with full SolarWinds exports for up-to-date status, as monitoring gaps may hide inactive partitions. If needed, I can add app-specific counts or a visual chart.